## WBS Version 02
BIM AND AUGMENTED REALITY
No. | Project Deliverables | Components | Tasks | Assumption/Constraints | Responsible Team member(s) | Tentative completion date
1 | Project Documentation | Software Design implementation | Research work |  | Aimen Shahid
|  | Analysis | Analyse the software and hardware requirments |  | Hamza Asif
|  | Architecture Patterns | Selection of Architecture design
Context Diagrams
2 | Image Processing
|  | Dataset preparation and preprocessing | Data collection | Manual data collection is required | Hamza Asif
|  |  | Reshaping of data | Architecture Drawings of building plan | Osama Ahmed
|  |  |  | Formats of Images are .JPG, .JPEG, .PNG | Aimen Shahid
Mustafa Rasheed
|  | Machine Learning | Training Model | Extraction vertices of shapes from images | Hamza Asif
|  |  | Feature Extraction from Images | Very closed line marked as noise | Osama Ahmed
|  |  | Fillertration of Images | Other then Shape all thing will be marked as noise
|  |  | Shape Detection | Structure is not under consideration
|  |  | Noise Detection and Removal | Windows will not be a part of learning model
|  | Database Design/ Data storing | Shape class for vertices manipulation | Noise free data | Hamza Asif
|  |  | Graph representation of vertices | Flat database will be use for saving vertices | Osama Ahmed
|  |  | Mid points extraction for 3D model | mark the vertices and join them as a graph structure
Calculate length of lines
Flat database design
|  | Hardware Requirments | GPU For model Training
High processing machine
3 | .Obj model/ modeling
|  | Convert 2D points into 3D points | Calculation the axes for 3D points | convert into .obj file format for rendering engine | Mustafa Rasheed
|  | Saving geometry for 3D model | Calculating the geometry | .obj model is generated and it can shown in any renderig engine | Mustaf Rasheed
|  |  |  | all the preprocssing for 3D modeling is completed in this part | Aimen Shahid
4 | 3D model and Animation
|  | Unity for rendering 3D model | loading all the geometry from .obj | 3D model will be saved in .obj model we have to just render in unity | Mustafa Rasheed
|  | Animation | Setting up the player for animation | Applying the animation and lightning | Aimen Shahid
|  |  | Camera and lightning | Setting up the player
5 | Deployment
|  | Web Application | Generation exe files |  | Hamza Asif
|  | Andrioid Application |  |  | Mustafa Rasheed
IOS application

## WBS Version 03
10Pearls FYP Accelerator Program - Work breakdown structure
BIM & AUGMENTED REALITY
No. | Project Deliverables | Components | Tasks | Assumption/Constraints | Responsible Team member(s) | Tentative completion date
1 | Training and Testing Images | DataBase Design | Data Collection | Restricted Map Images Available For Training
1.1 | Annotation File (.CSV) |  | Data Cleaning | Quality of Images is not so good
|  |  | Data Labeling | Images Are Complex
|  |  | Data Annotation | Hand-Made images not preferable
Format of Images are (.JPG, .JPEG, .PNG)
Only Architectural drawings of Building Plans
2 | Software List | System setup and configuration | Purchase Suitable GPU (RTX) | free vs. licensed software
3 | Hardware List |  | Install required softwares and tools
Decide right API and ML Platform
4 | Architectural Diagrams | UseCase Model/ Data Analysis | Draw Context Diagram
Draw Level 1 Diagram
Layered Architectural Diagram
5 | List of Algorithm | Image Processing Module | Line Detection | Lines close to the original lines will be marked as noise Structure will not be considered
| FlowCharts (optional) |  | Corner detection
Shape detection
6 | Trained CNN Model | AI module | Using TensorFlow and Keras
Transfer Learning
7 | .obj Loader/FBX | 3D modeling | Understand component of .obj
Understand and Apply Transformations
Datastructure (vertexList, FaceList)
save
8 | Test Cases | 3D Visualization | load .obj | File Size
|  |  | performace evaluation | Noise lines and corners handling
actual outcome vs. desired outcome
9 | 3D scene file | Basic 3D scene | tree datastructure
scene class
8 | Improved 3D scene | Light and shading | Ambient, diffuse, specular
Texturing
10 | Rendered Scene file (Player) | Rasterization | import model to rendering engine
camera animation
User interaction (optional)